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	Jasper and Newton County Continuum of Care
FY2026 CoC NOFO Local Competition Timeline 


All local submissions are due by 5:00 PM Central Time unless otherwise stated. Dates may be revised by the CoC if HUD issues changes or technical guidance.
HUD deadline check and local safeguards
	Checkpoint
	HUD / process requirement
	Local timeline response

	HUD NOFO deadline
	08/26/2026, 8:00 PM Eastern Time
	Local internal submission target is 08/21/2026; final HUD deadline retained as external deadline.

	15-day applicant notice
	Written notice must be sent no later than 15 days before the HUD deadline.
	Final priority list and written notifications scheduled for 08/11/2026.

	Public posting
	CoC Application, Priority Listing, and project listings should be publicly posted before final submission.
	Public posting scheduled for 08/17/2026; preserve dated screenshots.

	Local competition documentation
	Document public notice, scoring, ranking, appeals, threshold review, and application submission records.
	Timeline includes local review, appeal window, applicant revisions, and records checklist.


Local competition timeline
	Date
	Activity / deadline
	Responsible
	Place / notes

	Mon 6/1
	HUD releases FY2026 CoC Competition and YHDP Grants NOFO.
	HUD
	Grants.gov / e-snaps. Official HUD deadline is 08/26/2026.

	Tue 6/2
	Send NOFO release notice, links, and initial local competition alert to CoC membership, current project contacts, CoC Board, and interested stakeholders.
	Collaborative Applicant / CoC Lead
	Email and website. Include where updates will be posted.

	Tue 6/9
	Post project application timeline, Letter of Intent form, available application types, and local competition overview. Distribute by email and post to The Homeless Coalition website.
	Collaborative Applicant
	Website and email. Public notice should show local process and due dates.

	Tue 6/16
	Distribute renewal performance information, HMIS/comparable database reminders, and data quality review materials, if applicable.
	HMIS Lead / Collaborative Applicant
	Email; optional office hours. Allow time to correct data or explain data quality issues.

	Wed 6/16
	Rank and Review Committee updates forms, review process, local priorities, scoring tool, appeals process, and threshold screening plan.
	Rank and Review Committee
	Committee meeting. Handwritten local target date.

	By Fri 6/19
	Finalize and post local review/ranking procedures, score tool, LOI instructions, project application instructions, and applicant guidance.
	Collaborative Applicant / Rank and Review Chair
	Website and email. Keep screenshots for HUD documentation.

	Wed 6/24
	Letter of Intent due for all project types as applicable, including new, renewal, reallocation, DV bonus, consolidation, transition/replacement, planning, HMIS, and YHDP projects.
	Project Applicants
	Email submission. Use to plan local review workload and identify project types.

	By Fri 6/26
	Send local application packet, budget instructions, required attachments, and e-snaps guidance to applicants that submitted LOIs.
	Collaborative Applicant
	Email and website. Include contacts for technical questions.

	Mon 7/6
	NOFO applicant training and application instructions released; training available for new and renewal applicants.
	Collaborative Applicant; HMIS Lead
	Virtual / recorded. Cover e-snaps, local packet, scorecard, attachments, and deadlines.

	Wed 7/8
	Application portal/process opens for project applications and local packet submissions.
	Collaborative Applicant
	e-snaps and local submission instructions.

	Wed 7/15
	Optional applicant office hours and staff Q&A for process and technical questions. Staff may answer process questions but not project-specific scoring advice.
	Collaborative Applicant
	Virtual. Recommended final Q&A before submission week.

	Tue 7/21
	Agency project applications due in e-snaps. Applicants should submit the project application in e-snaps, export the PDF, and prepare the local packet.
	Project Applicants
	e-snaps. Handwritten local target date.

	Fri 7/24
	Applicant submits Rank and Review packet/forms to committee, including exported e-snaps PDF, local application, budget, attachments, match/source documentation, and threshold materials.
	Project Applicants
	Email, mail, or in person as directed. Handwritten local target date.

	Fri 7/24
	Projects that do not meet threshold review criteria are notified and are not advanced to Rank and Review Panel.
	Collaborative Applicant
	Written notice and/or phone call. Include reason for threshold decision.

	Sat 7/25 - Sun 8/2
	Rank and Review Committee reviews project applications, scorecards, local packets, budgets, and supporting documents independently.
	Rank and Review Committee
	Document review. Handwritten local review window.

	Mon 8/3
	Rank and Review Committee meeting to score, rank, and develop preliminary priority listing and funding recommendations.
	Rank and Review Committee
	In person or virtual. Handwritten priority-list date aligns with review window.

	Mon 8/3
	Distribute/post Preliminary Priority List and notify applicants of preliminary ranking, reductions, rejection, or reallocation recommendations.
	Collaborative Applicant / Rank and Review Chair
	Website and email. Starts appeal window.

	Tue 8/4
	Written appeals due to Rank and Review Committee Chair by 5:00 PM Central Time.
	Applicants
	Email to designated appeal contact. Handwritten local target date.

	Fri 8/7
	Appeals reviewed by Rank and Review Committee; appeal determinations documented.
	Rank and Review Committee
	Committee review. Handwritten local target date.

	Tue 8/11
	Final Priority List distributed/posted; written notice sent to all applicants identifying accepted and ranked, rejected, or reduced applications and, if applicable, reasons.
	Collaborative Applicant / Rank and Review Chair
	Website and email to all applicants. This preserves the HUD 15-day notice requirement.

	Wed 8/12 - Fri 8/14
	Applicants revise e-snaps project applications as directed due to recommended funding reductions, technical review clarification, appeal outcomes, or rank/review conditions.
	Project Applicants
	e-snaps. No changes after final applicant due date unless directed.

	Fri 8/14
	Final applicant deadline to complete project applications in e-snaps for Collaborative Applicant review.
	Project Applicants
	e-snaps. Recommended internal lock date.

	Mon 8/17
	Post draft CoC Consolidated Application, Priority Listing, and project listings for public review, including accepted/ranked, noncompetitive, and rejected projects as applicable.
	Collaborative Applicant
	The Homeless Coalition website; email notice. Keep dated screenshots.

	Thu 8/20
	CoC Board reviews and votes/approves final Consolidated Application package and Priority Listing for submission.
	CoC Board
	Board meeting / email vote. Address final comments before internal deadline.

	Fri 8/21
	Collaborative Applicant internal submission target: full application packet, CoC Application, Priority Listing, and ranked project applications ready/submitted in e-snaps.
	Collaborative Applicant
	e-snaps. Handwritten local target date; preserves buffer.

	Mon 8/24
	No substantive local changes after this date except urgent technical corrections. HUD technical questions become emergency-focused starting two days before the deadline.
	Collaborative Applicant
	e-snaps / HUD support. Use for receipt review and contingency.

	Wed 8/26
	HUD-determined final submission deadline for FY2026 CoC Consolidated Application package.
	Collaborative Applicant
	e-snaps. Due by 8:00 PM Eastern Time.
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